## Project Plan
FACIAL EXPRESSION CLASSIFICATION USING CNN
| FACIAL EXPRESSION CLASSIFICATION USING CNN | START DATE | END DATE | OVERALL PROGRESS
| GROUP SKIPZ | 2025-10-07 | 2026-11-08 | COMPLETED
TASK ID | PHASES/ACTIVITIES | START | FINISH | DURATION in days | COMMENTS | WBS ID | Work Package Name | Description | Deliverables | Resources Assigned | Duration Estimate | Acceptance Criteria | Estimated Cost (RM) | Calculation Note
1 | Requirement Gathering | 2025-10-07 | 2025-10-07 | 1 | Identify project goals, user needs, and system constraints. | 1.1.1 | Schedule Kick-off Meeting | Arrange and confirm a date and time for the initial project kick-off meeting with the team. | Confirmed calendar invite sent to the team. | Nadiah | 0.5 day (4 hours) | All core team members confirm attendance. | 80 | (4 hrs × RM 20)
[6 empty] | 1.1.2 | Define initial Scope and Goals | Document the high-level boundaries of the project, including the core problem statement. | Initial Scope Statement document. | Angelo | 0.5 day (4 hours) | Scope statement approved by the Project Manager (Angelo). | 80 | (4 hrs × RM 20)
[6 empty] | 1.2.1 | Document functional requirements | Identify and formally document what the system must do (e.g., classify 7 emotions, achieve 75% accuracy). | List of Functional Requirements (FRs). | Qasdina | 0.5 day (4 hours) | FRs cover all primary system functions. | 80 | (4 hrs × RM 20)
[6 empty] | 1.2.2 | Document non-functional requirements | Identify and formally document system performance constraints (e.g., processing time less than 500ms, security). | List of Non-Functional Requirements (NFRs). | Angelo | 0.5 day (4 hours) | NFRs address performance, security, and usability needs. | 80 | (4 hrs × RM 20)
[6 empty] | 1.3.1 | Obtain Stakeholder Sign-off | Review the gathered requirements with the project sponsor/client and obtain formal approval to proceed. | Requirements document signed/approved by Dr. Farhan Khan. | Angelo | 1 day | Formal acceptance received from Dr. Farhan Khan. | 160 | (8 hrs × RM 20)
2 | Data Collection | 2025-10-06 | 2025-10-08 | 3 | Gather relevant data from sources like surveys, datasets | 2.1.1 | Identify and select public datasets | Research and select suitable labeled facial expression datasets (e.g., FER-2013) that align with project goals. | List of potential datasets with licensing and size details. | Qasdina | 1 day | Selection finalized and approved by ML Engineer. | 160 | (8 hrs × RM 20)
[6 empty] | 2.2.1 | Download/Extract raw data and labels | Securely download the selected datasets and organize the raw image files and associated label metadata. | /data/raw/ folder containing all downloaded files. | Nadiah | 1 day | Data size meets initial target (e.g., 10,000 images). | 160 | (8 hrs × RM 20)
[6 empty] | 2.3.1 | Filter out low-quality/unlabeled images | Manually or programmatically inspect and remove corrupted, blurred, or improperly labeled images from the raw set. | Cleaned /data/cleaned/ folder. | Qasdina | 2 days | Data quality score (or error rate) meets acceptable standard. | 320 | (16 hrs × RM 20)
[6 empty] | 2.3.2 | Resize and normalize images | Apply standard preprocessing steps (e.g., resizing images to 48 x 48 pixels, pixel value normalization) for model input. | Script for image preprocessing created and tested. | Angelo | 1 day | Preprocessing script runs successfully on sample data. | 160 | (8 hrs × RM 20)
[6 empty] | 2.4.1 | Apply transformations (augmentation) | Use techniques like rotation, flipping, and zooming to expand the dataset to >= 10,000 labeled images. | /data/augmented/ folder with final target size. | Angelo | 1 day | Total dataset size reaches the 10,000 labeled image minimum objective. | 160 | (8 hrs × RM 20)
[6 empty] | 2.5.1 | Finalize and version control dataset | Split the dataset into training, validation, and test sets, and commit the final metadata/links to version control. | Versioned data_split.csv and final dataset folder structure. | Qasdina | 1 day | Splits are correctly balanced and committed to GitHub. | 160 | (8 hrs × RM 20)
3 | Model Design | 2025-10-09 | 2025-10-13 | 5 | Choose algorithms and structure the model to solve the defined problem. | 3.1.1 | Research and select CNN architectures | Study various CNN models (e.g., VGG, ResNet) and choose a baseline architecture for adaptation. | Document outlining the chosen baseline architecture and justification. | Angelo | 1 day | Selection is based on complexity vs. performance trade-offs. | 160 | (8 hrs × RM 20)
[6 empty] | 3.1.2 | Define layer structure and functions | Finalize the specific layer details, filter counts, and activation functions for the custom CNN model. | Model architecture diagram/code structure. | Angelo | 1 day | Model definition matches the required complexity for facial recognition. | 160 | (8 hrs × RM 20)
[6 empty] | 3.2.1 | Set up the ML environment | Install necessary libraries and frameworks (Python, TensorFlow/Keras, OpenCV) on the development machine. | Functional virtual environment file (requirements.txt). | Nadiah | 0.5 day (4 hours) | All required libraries are installed without dependency conflicts. | 80 | (4 hrs × RM 20)
[6 empty] | 3.2.2 | Secure necessary compute resources | Ensure access to GPU or cloud resources required for the heavy model training phase. | Confirmed access/allocation of GPU compute time. | Nadiah | 0.5 day (4 hours) | Compute resources are tested and verified for use. | 80 | (4 hrs × RM 20)
[6 empty] | 3.3.1 | Develop and commit initial model code | Write the initial Python code defining the chosen CNN architecture and commit it to GitHub. | model_architecture.py committed to the repo. | Qasdina | 1 day | Model code runs without syntax errors and prints a summary. | 160 | (8 hrs × RM 20)
4 | Model Training | 2025-10-14 | 2025-10-17 | 4 | Feed data into the model to learn patterns and optimize performance. | 4.1.1 | Define hyperparameters | Determine optimal values for learning rate, batch size, and the total number of training epochs. | List of training hyperparameters. | Angelo | 1 day | Parameters are chosen based on best practices and initial research. | 160 | (8 hrs × RM 20)
[6 empty] | 4.2.1 | Execute initial training run | Train the model for a few epochs on a small subset of the data to test the pipeline and parameters. | Initial training loss/accuracy curves generated. | Qasdina | 1 day | Training pipeline runs successfully without crashing. | 160 | (8 hrs × RM 20)
[6 empty] | 4.3.1 | Train the model on the full augmented dataset | Run the main training process using the final dataset and defined hyperparameters. | Final training log detailing loss and validation accuracy per epoch. | Nadiah | 3 days | Training is completed up to the defined epoch count. | 600 | (24 hrs × RM 20) + (RM 120 GPU Cost)
[6 empty] | 4.3.2 | Monitor loss and accuracy metrics | Track and plot the training and validation loss/accuracy to check for overfitting/underfitting. | Graphs of training/validation loss and accuracy over time. | Qasdina | 1 day | Training logs show reasonable convergence. | 160 | (8 hrs × RM 20)
[6 empty] | 4.4.1 | Save the best-performing model | Select the model checkpoint with the highest validation accuracy and save it in the required format. | Trained CNN Model File (.h5 or .pkl) committed to the repo. | Angelo | 1 day | Saved model file is verified to load correctly. | 160 | (8 hrs × RM 20)
5 | Model Evaluation | 2025-10-24 | 2025-10-26 | 3 | Assess model accuracy and reliability using test data and metrics. | 5.1.1 | Prepare the dedicated, unseen test dataset | Ensure the test dataset is completely separated from the training/validation sets and correctly formatted. | Final test dataset ready for inference. | Qasdina | 0.5 day (4 hours) | Test data integrity verified. | 80 | (4 hrs × RM 20)
[6 empty] | 5.2.1 | Calculate performance metrics | Run the trained model on the test data and calculate accuracy, precision, recall, and F1-score. | Table of key performance metrics. | Angelo | 1 day | All four key metrics (accuracy, precision, recall, F1) are calculated. | 160 | (8 hrs × RM 20)
[6 empty] | 5.3.1 | Analyze misclassified images | Identify and document patterns in the images the model failed to classify correctly (error analysis). | Log of model misclassifications and potential causes. | Nadiah | 1 day | At least 10 misclassified images analyzed. | 160 | (8 hrs × RM 20)
[6 empty] | 5.4.1 | Document final performance metrics | Write a concise evaluation summary comparing the results against the target objective of >= 75% accuracy. | Evaluation Summary document. | Angelo | 0.5 day (4 hours) | Document clearly states whether the >= 75% accuracy objective was met. | 80 | (4 hrs × RM 20)
6 | Dashboard Development | 2025-10-27 | 2025-10-30 | 4 | Build a user interface to visualize insights and monitor performance. | 6.1.1 | Create mockups of the classification output | Design the visual layout and user experience (UI/UX) for the prototype application/dashboard. | Wireframes or visual mockups of the user interface. | Nadiah | 1 day | Mockups reviewed and approved by the team. | 160 | (8 hrs × RM 20)
[6 empty] | 6.2.1 | Integrate the trained model with application | Build the API endpoint or backend logic that loads the trained model file and handles image input/output. | Backend module capable of returning model predictions. | Angelo | 1 day | Integration successfully loads and makes a prediction on a sample image. | 160 | (8 hrs × RM 20)
[6 empty] | 6.3.1 | Code the user interface elements | Implement the front-end components that display the image, the classification result, and prediction certainty. | Functional Prototype Application interface. | Qasdina | 1 day | UI is responsive and accurately reflects the design mockups. | 160 | (8 hrs × RM 20)
[6 empty] | 6.4.1 | Finalize the deployable application package | Prepare the prototype for sharing (e.g., containerize it, create an executable, or set up a cloud deployment). | Deployable prototype package. | Nadiah | 1 day | The prototype runs successfully on a separate target environment. | 160 | (8 hrs × RM 20)
7 | Testing & Validation | 2025-10-31 | 2025-11-02 | 3 | Ensure system functionality, correctness, and robustness. | 7.1.1 | Test individual components | Conduct unit tests on core modules (data handling, model prediction, dashboard display logic). | Unit test results log. | Qasdina | 1 day | All unit tests pass successfully. | 160 | (8 hrs × RM 20)
[6 empty] | 7.2.1 | Test end-to-end classification speed | Measure the system's total processing latency from image input to result display. | Measured latency time recorded. | Angelo | 1 day | Classification time is <= 500 milliseconds per image. | 160 | (8 hrs × RM 20)
[6 empty] | 7.3.1 | Conduct User Acceptance Testing (UAT) | Run the prototype with non-team stakeholders (e.g., Customer Service partner) to validate usability and fitness for purpose. | Feedback log from UAT participants. | Qasdina | 1 day | UAT stakeholders sign off on the prototype's usability. | 160 | (8 hrs × RM 20)
[6 empty] | 7.4.1 | Record all test results and sign off | Document all testing procedures, findings, and obtain the final team sign-off on system readiness. | Final Testing Documentation. | Nadiah | 1 day | All mandatory tests passed, and documentation is complete. | 160 | (8 hrs × RM 20)
8 | Report & Presentation | 2025-11-03 | 2025-11-08 | 6 | Summarize findings, methods, and results for stakeholders. | 8.1.1 | Document methodology and results | Write the bulk of the final project report, detailing the methods, results, and challenges. | Draft of the Final Project Report. | Angelo | 3 days | All sections of the report are drafted (Methodology, Results, Conclusion). | 480 | (24 hrs × RM 20)
[6 empty] | 8.2.1 | Design slides and talking points | Create the presentation slides and rehearse the content for the stakeholders. | Presentation slide deck. | Qasdina | 1 day | Slides are visually clear and cover all key findings. | 160 | (8 hrs × RM 20)
[6 empty] | 8.3.1 | Conduct a team review | Have all team members review the report and presentation for clarity, completeness, and errors. | Log of review comments and corresponding revisions. | All Team Members | 1 day | Report and presentation are free of major errors. | 480 | (8 hrs × 3 People × RM 20)
[6 empty] | 8.4.1 | Deliver final project assets | Finalize all deliverables (model, code, report) and conduct the final presentation. | Final Project Report & Performance Documentation. | All Team Members | 1 day | Final submission is complete and presentation is delivered. | 480 | (8 hrs × 3 People × RM 20)
[12 empty] | Total Cost (RM): | 6840

## Week 05 – Cost & Resources (hidden)
WBS ID | Task | Duration (Hrs) | Resource Name | Rate (RM) | Total Cost (RM) | Assigned Team Member
1 | Requirement Gathering | 24 |  |  | 600
1.1.1 | Schedule Kick-off Meeting | 4 | Team Member | 25/hr | 100 | Nadiah
1.1.2 | Define initial Scope and Goals | 4 | Team Member | 25/hr | 100 | Angelo
1.2.1 | Document functional requirements | 4 | Team Member | 25/hr | 100 | Qasdina
1.2.2 | Document non-functional requirements | 4 | Team Member | 25/hr | 100 | Angelo
1.3.1 | Obtain Stakeholder Sign-off | 8 | Team Member | 25/hr | 200 | Angelo
2 | Data Collection | 56 |  |  | 1420
2.1.1 | Identify and select public datasets | 8 | Research Assistant | 30/hr | 240 | Qasdina
2.2.1 | Download/Extract raw data and labels | 8 | Storage/Server | 100 flat | 100 | Nadiah
2.3.1 | Filter out low-quality/unlabeled images | 16 | Research Assistant | 30/hr | 480 | Qasdina
2.3.2 | Resize and normalize images | 8 | Team Member | 25/hr | 200 | Angelo
2.4.1 | Apply transformations (augmentation) | 8 | Team Member | 25/hr | 200 | Angelo
2.5.1 | Finalize and version control dataset | 8 | Team Member | 25/hr | 200 | Qasdina
3 | Model Design | 32 |  |  | 800
3.1.1 | Research and select CNN architectures | 8 | Team Member | 25/hr | 200 | Angelo
3.1.2 | Define layer structure and functions | 8 | Team Member | 25/hr | 200 | Angelo
3.2.1 | Set up the ML environment | 4 | Software (TensorFlow) | 100 flat | 100 | Nadiah
3.2.2 | Secure necessary compute resources | 4 | Team Member | 25/hr | 100 | Nadiah
3.3.1 | Develop and commit initial model code | 8 | Team Member | 25/hr | 200 | Qasdina
4 | Model Training | 48 |  |  | 920
4.1.1 | Define hyperparameters | 8 | Team Member | 25/hr | 200 | Angelo
4.2.1 | Execute initial training run | 8 | GPU Instance | 10/hr | 80 | Qasdina
4.3.1 | Train the model on the full augmented dataset | 24 | GPU Instance | 10/hr | 240 | Nadiah
4.3.2 | Monitor loss and accuracy metrics | 8 | Team Member | 25/hr | 200 | Qasdina
4.4.1 | Save the best-performing model | 8 | Team Member | 25/hr | 200 | Angelo
5 | Model Evaluation | 24 |  |  | 600
5.1.1 | Prepare the dedicated, unseen test dataset | 4 | Team Member | 25/hr | 100 | Qasdina
5.2.1 | Calculate performance metrics | 8 | Team Member | 25/hr | 200 | Angelo
5.3.1 | Analyze misclassified images | 8 | Team Member | 25/hr | 200 | Nadiah
5.4.1 | Document final performance metrics | 4 | Team Member | 25/hr | 100 | Angelo
6 | Dashboard Development | 32 |  |  | 700
6.1.1 | Create mockups of the classification output | 8 | Team Member | 25/hr | 200 | Nadiah
6.2.1 | Integrate the trained model with application | 8 | Team Member | 25/hr | 200 | Angelo
6.3.1 | Code the user interface elements | 8 | Front-end Tools | 100 flat | 100 | Qasdina
6.4.1 | Finalize the deployable package | 8 | Team Member | 25/hr | 200 | Nadiah
7 | Testing & Validation | 32 |  |  | 800
7.1.1 | Test individual components | 8 | Team Member | 25/hr | 200 | Qasdina
7.2.1 | Test end-to-end classification speed | 8 | Team Member | 25/hr | 200 | Angelo
7.3.1 | Conduct User Acceptance Testing (UAT) | 8 | Team Member | 25/hr | 200 | Qasdina
7.4.1 | Record all test results and sign off | 8 | Team Member | 25/hr | 200 | Nadiah
8 | Report & Presentation | 48 |  |  | 1200
8.1.1 | Document methodology and results | 24 | Team Member | 25/hr | 600 | Angelo
8.2.1 | Design slides and talking points | 8 | Team Member | 25/hr | 200 | Qasdina
8.3.1 | Conduct a team review | 8 | Team Member | 25/hr | 200 | All Team Members
8.4.1 | Deliver final project assets | 8 | Team Member | 25/hr | 200 | All Team Members

## Sheet4 (hidden)
WBS ID | Task | Duration (Hrs) | Resource Type | Rate (RM) | Total Cost (RM) | Resources Assigned
Project Total |  | 328 |  |  | 6140
1.1.1 | Schedule Kick-off Meeting | 4 | Team Member | 25/hr | 100 | Nadiah | 7040
1.1.2 | Define initial Scope and Goals | 4 | Team Member | 25/hr | 100 | Angelo
1.2.1 | Document functional requirements | 4 | Team Member | 25/hr | 100 | Qasdina
1.2.2 | Document non-functional requirements | 4 | Team Member | 25/hr | 100 | Angelo
1.3.1 | Obtain Stakeholder Sign-off | 8 | Team Member | 25/hr | 200 | Angelo
2.1.1 | Identify and select public datasets | 8 | Research Assistant | 30/hr | 240 | Qasdina
2.2.1 | Download/Extract raw data and labels | 8 | Storage/Server | 100 flat | 100 | Nadiah
2.3.1 | Filter out low-quality/unlabeled images | 16 | Research Assistant | 30/hr | 480 | Qasdina
2.3.2 | Resize and normalize images | 8 | Team Member | 25/hr | 200 | Angelo
2.4.1 | Apply transformations (augmentation) | 8 | Team Member | 25/hr | 200 | Angelo
2.5.1 | Finalize and version control dataset | 8 | Team Member | 25/hr | 200 | Qasdina
3.1.1 | Research and select CNN architectures | 8 | Team Member | 25/hr | 200 | Angelo
3.1.2 | Define layer structure and functions | 8 | Team Member | 25/hr | 200 | Angelo
3.2.1 | Set up the ML environment | 4 | Software (TensorFlow) | 100 flat | 100 | Nadiah
3.2.2 | Secure necessary compute resources | 4 | Team Member | 25/hr | 100 | Nadiah
3.3.1 | Develop and commit initial model code | 8 | Team Member | 25/hr | 200 | Qasdina
4.1.1 | Define hyperparameters | 8 | Team Member | 25/hr | 200 | Angelo
4.2.1 | Execute initial training run | 8 | GPU Instance | 10/hr | 80 | Qasdina
4.3.1 | Train the model on the full augmented dataset | 24 | GPU Instance | 10/hr | 240 | Nadiah
4.3.2 | Monitor loss and accuracy metrics | 8 | Team Member | 25/hr | 200 | Qasdina
4.4.1 | Save the best-performing model | 8 | Team Member | 25/hr | 200 | Angelo
5.1.1 | Prepare the dedicated, unseen test dataset | 4 | Team Member | 25/hr | 100 | Qasdina
5.2.1 | Calculate performance metrics | 8 | Team Member | 25/hr | 200 | Angelo
5.3.1 | Analyze misclassified images | 8 | Team Member | 25/hr | 200 | Nadiah
5.4.1 | Document final performance metrics | 4 | Team Member | 25/hr | 100 | Angelo
6.1.1 | Create mockups of the classification output | 8 | Team Member | 25/hr | 200 | Nadiah
6.2.1 | Integrate the trained model with application | 8 | Team Member | 25/hr | 200 | Angelo
6.3.1 | Code the user interface elements | 8 | Front-end Tools | 100 flat | 100 | Qasdina
6.4.1 | Finalize the deployable package | 8 | Team Member | 25/hr | 200 | Nadiah
7.1.1 | Test individual components | 8 | Team Member | 25/hr | 200 | Qasdina
7.2.1 | Test end-to-end classification speed | 8 | Team Member | 25/hr | 200 | Angelo
7.3.1 | Conduct User Acceptance Testing (UAT) | 8 | Team Member | 25/hr | 200 | Qasdina
7.4.1 | Record all test results and sign off | 8 | Team Member | 25/hr | 200 | Nadiah
8.1.1 | Document methodology and results | 24 | Team Member | 25/hr | 600 | Angelo
8.2.1 | Design slides and talking points | 8 | Team Member | 25/hr | 200 | Qasdina
8.3.1 | Conduct a team review | 8 | Team Member | 25/hr | 200 | All Team Members
8.4.1 | Deliver final project assets | 8 | Team Member | 25/hr | 200 | All Team Members

## WBS Dictionary
WBS ID | Work Package Name | Description | Deliverables | Resources Assigned | Duration Estimate | Acceptance Criteria
1.1.1 | Schedule Kick-off Meeting | Arrange and confirm a date and time for the initial project kick-off meeting. | Confirmed calendar invite sent to the team. | Nadiah | 0.5 day (4 hours) | All core team members confirm attendance.
1.1.2 | Define initial Scope and Goals | Document the high-level boundaries of the project, including the core problem statement. | Initial Scope Statement document. | Angelo | 0.5 day (4 hours) | Scope statement approved by the Project Manager (Angelo).
1.2.1 | Document functional requirements | Identify and formally document what the system must do (e.g., classify 7 emotions, achieve 75% accuracy). | List of Functional Requirements (FRs). | Qasdina | 0.5 day (4 hours) | FRs cover all primary system functions.
1.2.2 | Document non-functional requirements | Identify and formally document system performance constraints (e.g., processing time <=500 ms, security). | List of Non-Functional Requirements (NFRs). | Angelo | 0.5 day (4 hours) | NFRs address performance, security, and usability needs.
1.3.1 | Obtain Stakeholder Sign-off | Review the gathered requirements with the project sponsor/client and obtain formal approval. | Requirements document signed/approved by Dr. Farhan Khan. | Angelo | 1 day | Formal acceptance received from Dr. Farhan Khan.
2.1.1 | Identify and select public datasets | Research and select suitable labeled facial expression datasets. | List of potential datasets with licensing and size details. | Qasdina | 1 day | Selection finalized and approved by ML Engineer.
2.2.1 | Download/Extract raw data and labels | Securely download the selected datasets and organize the raw image files and labels. | /data/raw/ folder containing all downloaded files. | Nadiah | 1 day | Data size meets initial target (e.g., 10,000 images).
2.3.1 | Filter out low-quality/unlabeled images | Inspect and remove corrupted, blurred, or improperly labeled images from the raw set. | Cleaned /data/cleaned/ folder. | Qasdina | 2 days | Data quality score (or error rate) meets acceptable standard.
2.3.2 | Resize and normalize images | Apply standard preprocessing steps (e.g., resizing to 48 x 48 pixels, pixel value normalization) for model input. | Script for image preprocessing created and tested. | Angelo | 1 day | Preprocessing script runs successfully on sample data.
2.4.1 | Apply transformations (augmentation) | Use techniques like rotation, flipping, and zooming to expand the dataset to >=10,000 labeled images. | /data/augmented/ folder with final target size. | Angelo | 1 day | Total dataset size reaches the 10,000 labeled image minimum objective.
2.5.1 | Finalize and version control dataset | Split the dataset into training, validation, and test sets, and commit the final metadata. | Versioned data_split.csv and final dataset folder structure. | Qasdina | 1 day | Splits are correctly balanced and committed to GitHub.
3.1.1 | Research and select CNN architectures | Study various CNN models and choose a baseline architecture for adaptation. | Document outlining the chosen baseline architecture and justification. | Angelo | 1 day | Selection is based on complexity vs. performance trade-offs.
3.1.2 | Define layer structure and functions | Finalize the specific layer details, filter counts, and activation functions for the custom CNN model. | Model architecture diagram/code structure. | Angelo | 1 day | Model definition matches the required complexity for facial recognition.
3.2.1 | Set up the ML environment | Install necessary libraries and frameworks (Python, TensorFlow/Keras, OpenCV) on the development machine. | Functional virtual environment file (requirements.txt). | Nadiah | 0.5 day (4 hours) | All required libraries are installed without dependency conflicts.
3.2.2 | Secure necessary compute resources | Ensure access to GPU or cloud resources required for the heavy model training phase. | Confirmed access/allocation of GPU compute time. | Nadiah | 0.5 day (4 hours) | Compute resources are tested and verified for use.
3.3.1 | Develop and commit initial model code | Write the initial Python code defining the chosen CNN architecture and commit it to GitHub. | model_architecture.py committed to the repo. | Qasdina | 1 day | Model code runs without syntax errors and prints a summary.
4.1.1 | Define hyperparameters | Determine optimal values for learning rate, batch size, and the total number of training epochs. | List of training hyperparameters. | Angelo | 1 day | Parameters are chosen based on best practices and initial research.
4.2.1 | Execute initial training run | Train the model for a few epochs on a small subset of the data to test the pipeline and parameters. | Initial training loss/accuracy curves generated. | Qasdina | 1 day | Training pipeline runs successfully without crashing.
4.3.1 | Train the model on the full augmented dataset | Run the main training process using the final dataset and defined hyperparameters. | Final training log detailing loss and validation accuracy per epoch. | Nadiah | 3 days | Training is completed up to the defined epoch count.
4.3.2 | Monitor loss and accuracy metrics | Track and plot the training and validation loss/accuracy to check for overfitting/underfitting. | Graphs of training/validation loss and accuracy over time. | Qasdina | 1 day | Training logs show reasonable convergence.
4.4.1 | Save the best-performing model | Select the model checkpoint with the highest validation accuracy and save it in the required format. | Trained CNN Model File (.h5 or .pkl) committed to the repo. | Angelo | 1 day | Saved model file is verified to load correctly.
5.1.1 | Prepare the dedicated, unseen test dataset | Ensure the test dataset is completely separated from the training/validation sets and correctly formatted. | Final test dataset ready for inference. | Qasdina | 0.5 day (4 hours) | Test data integrity verified.
5.2.1 | Calculate performance metrics | Run the trained model on the test data and calculate accuracy, precision, recall, and F1-score. | Table of key performance metrics. | Angelo | 1 day | All four key metrics (accuracy, precision, recall, F1) are calculated.
5.3.1 | Analyze misclassified images | Identify and document patterns in the images the model failed to classify correctly. | Log of model misclassifications and potential causes. | Nadiah | 1 day | At least 10 misclassified images analyzed.
5.4.1 | Document final performance metrics | Write a concise evaluation summary comparing the results against the target objective of >=75% accuracy. | Evaluation Summary document. | Angelo | 0.5 day (4 hours) | Document clearly states whether the >= 75% accuracy objective was met.
6.1.1 | Create mockups of the classification output | Design the visual layout and user experience (UI/UX) for the prototype application/dashboard. | Wireframes or visual mockups of the user interface. | Nadiah | 1 day | Mockups reviewed and approved by the team.
6.2.1 | Integrate the trained model with application | Build the API endpoint or backend logic that loads the trained model file and handles image input/output. | Backend module capable of returning model predictions. | Angelo | 1 day | Integration successfully loads and makes a prediction on a sample image.
6.3.1 | Code the user interface elements | Implement the front-end components that display the image, the classification result, and prediction certainty. | Functional Prototype Application interface. | Qasdina | 1 day | UI is responsive and accurately reflects the design mockups.
6.4.1 | Finalize the deployable application package | Prepare the prototype for sharing (e.g., containerize it, create an executable, or set up a cloud deployment). | Deployable prototype package. | Nadiah | 1 day | The prototype runs successfully on a separate target environment.
7.1.1 | Test individual components | Conduct unit tests on core modules (data handling, model prediction, dashboard display logic). | Unit test results log. | Qasdina | 1 day | All unit tests pass successfully.
7.2.1 | Test end-to-end classification speed | Measure the system's total processing latency from image input to result display. | Measured latency time recorded. | Angelo | 1 day | Classification time is <= 500 milliseconds per image.
7.3.1 | Conduct User Acceptance Testing (UAT) | Run the prototype with non-team stakeholders to validate usability and fitness for purpose. | Feedback log from UAT participants. | Qasdina | 1 day | UAT stakeholders sign off on the prototype's usability.
7.4.1 | Record all test results and sign off | Document all testing procedures, findings, and obtain the final team sign-off on system readiness. | Final Testing Documentation. | Nadiah | 1 day | All mandatory tests passed, and documentation is complete.
8.1.1 | Document methodology and results | Write the bulk of the final project report, detailing the methods, results, and challenges. | Draft of the Final Project Report. | Angelo | 3 days | All sections of the report are drafted (Methodology, Results, Conclusion).
8.2.1 | Design slides and talking points | Create the presentation slides and rehearse the content for the stakeholders. | Presentation slide deck. | Qasdina | 1 day | Slides are visually clear and cover all key findings.
8.3.1 | Conduct a team review | Have all team members review the report and presentation for clarity, completeness, and errors. | Log of review comments and corresponding revisions. | All Team Members | 1 day | Report and presentation are free of major errors.
8.4.1 | Deliver final project assets | Finalize all deliverables (model, code, report) and conduct the final presentation. | Final Project Report & Performance Documentation. | All Team Members | 1 day | Final submission is complete and presentation is delivered.