## Sheet1
SKIPZ: Facial Expression Recognition using CNN
Project Name | Facial Expression Recognition using CNN
Project Sponsor | Dr. Farhan Khan
Project Manager | Angelo A/L Govindasamy
Date | 2025-10-27
Problem Statement | Facial expressions are vital for understanding human emotions and improving communication. However, accurately identifying these expressions remains challenging. This project develops a CNN-based AI model that classifies facial expressions into various emotions, aiming to enhance emotion recognition systems for applications like security, customer service, and mental health assessment.
Project Objectives | • Collect and prepare a dataset of at least 10,000 labeled facial expression images
• Develop and train a CNN model capable of classifying facial expressions with minimum 75% accuracy
• Integrate the model into a prototype that performs expression classification within 500 milliseconds per image
• Thoroughly evaluate the model's performance and document the project's development and results
Key Deliverables | • Curated and Augmented Dataset
• Trained CNN Model File (.h5 or .pkl)
• Functional Prototype Application
• Final Project Report & Performance Documentation
Key Stakeholders | • Sponsor: Dr. Farhan Khan
• Project Team: Data Scientist, ML Engineer, Software Developer
• End-Users: Customer Service Department, Security Partners
• Technical Reviewers: AI Research Team
Tools & Integration | • MS Project for scheduling
• GitHub for version control
• MS Teams for collaboration

## Sheet2
Task Name